## Working route
Blackboard Group No 2 Class NGG | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | PM class date | =====> | 2022-07-27 | Tuesday Jul.26 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-08-19 | PM class plus | 0 | days
Each group member | Project Mgmt Activity | share with Group | 1 | Thursday Jul.28 | DONE
Group Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Friday Jul.29 | DONE | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 1 | Tuesday Aug.2 | DONE | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1 | Sunday Aug.7 | DONE | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Sunday Aug.14 | DONE | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. |  | Tuesday Aug.16 | TO DO
| request review from professor | Group's Team Channel > Files > click ..._Plan.xlsx > click Conversation (top right) > @your_professor "Please review." |  | Saturday Jul.30 | DONE | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Tuesday Aug.2 | DONE | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." | 1 | Sunday Aug.7 | DONE | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Sunday Aug.14 | DONE
Martin Fundamentals | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Have a group meeting and agree on the tasks and group leader. | 1.5 | Friday Jul.29 | DONE | Understand the Fundamentals module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the fundamentals.h and fundamentals.c, fundamentals-test-cases.xlsx and fundamentals-testing.txt | 2 | Wednesday Aug.3 | DONE | Understand the Fundamentals module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the fundamentals.h and fundamentals.c, fundamentals-test-cases.xlsx, fundamentals-testing.txt, and fundamentals-git-log.txt | 2 | Monday Aug.8 | DONE | Understand the Fundamentals module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the fundamentals.h and fundamentals.c, fundamentals-test-cases.xlsx, fundamentals-testing.txt, and fundamentals-git-log.txt | 2 | Monday Aug.15 | DONE |  |  |  | Wednesday Aug.17
Nimit Manipulations | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Have a group meeting and agree on the tasks and group leader. | 1.5 | Friday Jul.29 | DONE | Understand the Manipulations module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the manipulations.h and manipulations.c, manipulations-test-cases.xlsx and manipulations-testing.txt | 2 | Wednesday Aug.3 | DONE | Understand the Manipulations module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the manipulations.h and manipulations.c, manipulations-test-cases.xlsx, manipulations-testing.txt, and manipulations-git-log.txt | 2 | Monday Aug.8 | DONE | Understand the Manipulations module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the manipulations.h and manipulations.c, manipulations-test-cases.xlsx, manipulations-testing.txt, and manipulations-git-log.txt | 2 | Monday Aug.15 | DONE |  |  |  | Wednesday Aug.17
Raymond Tokenizing | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Have a group meeting and agree on the tasks and group leader. | 1.5 | Friday Jul.29 | DONE | Understand the Tokenizing module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the tokenizing.h and tokenizing.c, tokenizing-test-cases.xlsx and tokenizing-testing.txt | 2 | Wednesday Aug.3 | DONE | Understand the Tokenizing module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the tokenizing.h and tokenizing.c, tokenizing-test-cases.xlsx, tokenizing-testing.txt, and tokenizing-git-log.txt | 2 | Monday Aug.8 | DONE | Understand the Tokenizing module. Add comments to understand what the line of code is doing. Run the code and do testing. | Create the tokenizing.h and tokenizing.c, tokenizing-test-cases.xlsx, tokenizing-testing.txt, and tokenizing-git-log.txt | 2 | Monday Aug.15 | DONE |  |  |  | Wednesday Aug.17
Varun Conversions Group Leader | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | Have a group meeting and agree on the tasks and group leader. | 1.5 | Saturday Jul.30 | DONE | Understand the Conversions module. Add comments to understand what the line of code is doing. Run the code and do testing. Combine the 4 modules, run and do testing. | Create the conversions.h and conversions.c, conversions-test-cases.xlsx and conversions-testing.txt. Create the main.c, min-test-cases.xlsx and main-testing.txt | 4 | Thursday Aug.4 | DONE | Understand the Conversions module. Add comments to understand what the line of code is doing. Run the code and do testing. Combine the 4 modules, run and do testing. | Create the conversions.h and conversions.c, conversions-test-cases.xlsx, conversions-testing.txt, and conversions-git-log.txt. Create the main.c, min-test-cases.xlsx and main-testing.txt | 4 | Tuesday Aug.9 | DONE | Understand the Conversions module. Add comments to understand what the line of code is doing. Run the code and do testing. Combine the 4 modules, run and do testing. | Create the conversions.h and conversions.c, conversions-test-cases.xlsx, conversions-testing.txt, and conversions-git-log.txt. Create the main.c, min-test-cases.xlsx and main-testing.txt | 4 | Tuesday Aug.16 | DONE |  |  |  | Thursday Aug.18
|  |  |  | milestone |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard | DONE |  |  |  | ABSOLUTE DEADLINE
[7 empty] | What is the group's criteria for acceptance of development (individual files) when promoted to integration (Teams group Files) -- remember the SDLC and Version Control flow? What is definition of done / good enough? Who decides that? | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.